## Standup Log
Date | Sprint | Role | Work Completed | Next Steps | Blockers
2026-07-11 | Sprint 1 | Business Analyst | Formulated requirements and drafted initial solution brief (5 target classes, YOLOv8 vehicle filtering, crop padding, 0.75 threshold). | Prepare user stories for Phase 5 integration testing. | None
2026-07-11 | Sprint 1 | UX Designer | Designed layout wireframes for Dashboard and Live Camera view. Produced high-fidelity Mock Screen specifications (Obsidian Dark palette, glassmorphism CSS styling, hover interactions). | Review UI implementations to ensure design fidelity. | None
2026-07-11 | Sprint 1 | Solution Architect | Reviewed and approved UX wireframe layout for technical execution. Validated canvas overlays and 10-15 FPS frame throttling constraints. | Support integration of Django endpoints with Angular UI. | None
2026-07-11 | Sprint 1 | ML Engineer | Audited dataset (Audi: 92, BMW: 84, Jeep: 85, Suzuki: 80, Tesla: 77). Configured ResNet50 classifier training scripts and completed Epoch 10 Checkpoint. | Track remaining checkpoints. Epoch 20 scheduled for 06:51:47 AM. | None
2026-07-11 | Sprint 1 | Backend Developer | Initialized Django project, configured settings.py/urls.py, installed dependencies (Django, REST framework, OpenCV, Ultralytics). Created views.py with YOLOv8 detection and ResNet50 hooks. | Integrate best ResNet50 model weights file once training finishes. | None
2026-07-11 | Sprint 1 | Frontend Developer | Initialized Angular workspace, installed npm packages. Created CarDetectionService, router routes, and implemented layouts/templates for Dashboard and LiveCamera components. | Spin up local Angular server for integration testing. | None
2026-07-11 | Sprint 1 | Scrum Master | Facilitated Scrum Call Day 1, logged team progress, and created standup tracking files (markdown and Excel logs). | Coordinate parallel testing and integration once model training is completed. | None
2026-07-11 | Sprint 1 | Business Analyst | Formulated requirements and drafted initial solution brief (5 target classes, YOLOv8 vehicle filtering, crop padding, 0.75 threshold). | Prepare user stories for Phase 5 integration testing. | None
2026-07-11 | Sprint 1 | UX Designer | Designed layout wireframes for Dashboard and Live Camera view. Produced high-fidelity Mock Screen specifications (Obsidian Dark palette, glassmorphism CSS styling, hover interactions). | Review UI implementations to ensure design fidelity. | None
2026-07-11 | Sprint 1 | Solution Architect | Reviewed and approved UX wireframe layout for technical execution. Validated canvas overlays and 10-15 FPS frame throttling constraints. | Support integration of Django endpoints with Angular UI. | None
2026-07-11 | Sprint 1 | ML Engineer | Audited dataset (Audi: 92, BMW: 84, Jeep: 85, Suzuki: 80, Tesla: 77). Configured ResNet50 classifier training scripts and completed Epoch 10 & 20 Checkpoints. | Track remaining checkpoints. Epoch 30 scheduled for 07:10:24 AM. | None
2026-07-11 | Sprint 1 | Backend Developer | Initialized Django project, configured settings.py/urls.py, installed dependencies (Django, REST framework, OpenCV, Ultralytics). Created views.py with YOLOv8 detection and ResNet50 hooks. | Integrate best ResNet50 model weights file once training finishes. | None
2026-07-11 | Sprint 1 | Frontend Developer | Initialized Angular workspace, installed npm packages. Created CarDetectionService, router routes, and implemented layouts/templates for Dashboard and LiveCamera components. | Spin up local Angular server for integration testing. | None
2026-07-11 | Sprint 1 | Scrum Master | Facilitated Scrum Call Day 1, logged team progress, and created standup tracking files (markdown and Excel logs). | Coordinate parallel testing and integration once model training is completed. | None
2026-07-11 | Sprint 1 | Business Analyst | Formulated requirements and drafted initial solution brief (5 target classes, YOLOv8 vehicle filtering, crop padding, 0.75 threshold). | Prepare user stories for Phase 5 integration testing. | None
2026-07-11 | Sprint 1 | UX Designer | Designed layout wireframes for Dashboard and Live Camera view. Produced high-fidelity Mock Screen specifications (Obsidian Dark palette, glassmorphism CSS styling, hover interactions). | Review UI implementations to ensure design fidelity. | None
2026-07-11 | Sprint 1 | Solution Architect | Reviewed and approved UX wireframe layout for technical execution. Validated canvas overlays and 10-15 FPS frame throttling constraints. | Support integration of Django endpoints with Angular UI. | None
2026-07-11 | Sprint 1 | ML Engineer | Audited dataset (Audi: 92, BMW: 84, Jeep: 85, Suzuki: 80, Tesla: 77). Configured ResNet50 classifier training scripts and completed Epoch 10, 20 & 30 Checkpoints. | Track remaining checkpoints. Epoch 40 scheduled for 07:25:34 AM. | None
2026-07-11 | Sprint 1 | Backend Developer | Initialized Django project, configured settings.py/urls.py, installed dependencies (Django, REST framework, OpenCV, Ultralytics). Created views.py with YOLOv8 detection and ResNet50 hooks. | Integrate best ResNet50 model weights file once training finishes. | None
2026-07-11 | Sprint 1 | Frontend Developer | Initialized Angular workspace, installed npm packages. Created CarDetectionService, router routes, and implemented layouts/templates for Dashboard and LiveCamera components. | Spin up local Angular server for integration testing. | None
2026-07-11 | Sprint 1 | Scrum Master | Facilitated Scrum Call Day 1, logged team progress, and created standup tracking files (markdown and Excel logs). | Coordinate parallel testing and integration once model training is completed. | None
2026-07-11 | Sprint 1 | Business Analyst | Formulated requirements and drafted initial solution brief (5 target classes, YOLOv8 vehicle filtering, crop padding, 0.75 threshold). | Prepare user stories for Phase 5 integration testing. | None
2026-07-11 | Sprint 1 | UX Designer | Designed layout wireframes for Dashboard and Live Camera view. Produced high-fidelity Mock Screen specifications (Obsidian Dark palette, glassmorphism CSS styling, hover interactions). | Review UI implementations to ensure design fidelity. | None
2026-07-11 | Sprint 1 | Solution Architect | Reviewed and approved UX wireframe layout for technical execution. Validated canvas overlays and 10-15 FPS frame throttling constraints. | Support integration of Django endpoints with Angular UI. | None
2026-07-11 | Sprint 1 | ML Engineer | Audited dataset (Audi: 92, BMW: 84, Jeep: 85, Suzuki: 80, Tesla: 77). Configured ResNet50 classifier training scripts and completed Epoch 10, 20, 30 & 40 Checkpoints. | Track final checkpoint. Epoch 50 scheduled for 07:39:35 AM. | None
2026-07-11 | Sprint 1 | Backend Developer | Initialized Django project, configured settings.py/urls.py, installed dependencies (Django, REST framework, OpenCV, Ultralytics). Created views.py with YOLOv8 detection and ResNet50 hooks. | Integrate best ResNet50 model weights file once training finishes. | None
2026-07-11 | Sprint 1 | Frontend Developer | Initialized Angular workspace, installed npm packages. Created CarDetectionService, router routes, and implemented layouts/templates for Dashboard and LiveCamera components. | Spin up local Angular server for integration testing. | None
2026-07-11 | Sprint 1 | Scrum Master | Facilitated Scrum Call Day 1, logged team progress, and created standup tracking files (markdown and Excel logs). | Coordinate parallel testing and integration once model training is completed. | None
2026-07-11 | Sprint 1 | Business Analyst | Formulated requirements and drafted initial solution brief (5 target classes, YOLOv8 vehicle filtering, crop padding, 0.75 threshold). | Prepare user stories for Phase 5 integration testing. | None
2026-07-11 | Sprint 1 | UX Designer | Designed layout wireframes for Dashboard and Live Camera view. Produced high-fidelity Mock Screen specifications (Obsidian Dark palette, glassmorphism CSS styling, hover interactions). | Review UI implementations to ensure design fidelity. | None
2026-07-11 | Sprint 1 | Solution Architect | Reviewed and approved UX wireframe layout for technical execution. Validated canvas overlays and 10-15 FPS frame throttling constraints. | Support integration of Django endpoints with Angular UI. | None
2026-07-11 | Sprint 1 | ML Engineer | Audited dataset (Audi: 92, BMW: 84, Jeep: 85, Suzuki: 80, Tesla: 77). Configured ResNet50 classifier training scripts and completed all 50 Epochs. Model achieved 93.75% test accuracy. | Idle / Support QA and integration verification. | None
2026-07-11 | Sprint 1 | Backend Developer | Initialized Django project, configured settings.py/urls.py, installed dependencies. Created views.py with YOLOv8 detection and ResNet50 hooks. Completed model integration with verified best ResNet50 model weights. | Support QA end-to-end integration testing. | None
2026-07-11 | Sprint 1 | Frontend Developer | Initialized Angular workspace, installed npm packages. Created CarDetectionService, router routes, and implemented layouts/templates for Dashboard and LiveCamera components. | Support QA end-to-end integration testing. | None
2026-07-11 | Sprint 1 | Scrum Master | Facilitated Scrum Call Day 1, logged team progress, and created standup tracking files (markdown and Excel logs). Verified successful end-to-end integration API testing. | Support final CEO review and project release gates. | None