## Story Tracker
Date | Story ID | Role | Story Title | Description | Status | Blocker Note
2026-07-11 | ST-01 | Business Analyst | Solution Brief Formulation | Formulate requirements and write the solution proposal brief for YOLOv8 detection & ResNet50 classification. | DONE | -
2026-07-11 | ST-02 | UX Designer | UX Wireframe Layouts Design | Create layout wireframes for the Upload Dashboard and Live Monitoring views. | DONE | -
2026-07-11 | ST-03 | UX Designer | High-Fidelity Mock Screens Design | Define design tokens, HSL colors, Obsidian Dark styling guidelines, and card hover interactions. | DONE | -
2026-07-11 | ST-04 | Solution Architect | Wireframe Feasibility Audit | Review UX wireframes for coordinates mapping scalability and live frame rate throttling bounds. | DONE | -
2026-07-11 | ST-05 | ML Engineer | ResNet50 Classifier Training | Audit dataset splits, setup torch configurations, and run training comparison for 10/20/30/40/50 epochs. | IN PROGRESS | -
2026-07-11 | ST-06 | Backend Developer | Django API & Views Setup | Initialize django backend, write REST endpoints, and implement YOLOv8 detection/crop views. | READY FOR REVIEW | Awaiting final ResNet50 model weights to complete model integration.
2026-07-11 | ST-07 | Frontend Developer | Angular UI Components Coding | Initialize Angular app, build CarDetectionService, Dashboard upload views, and LiveCamera canvas drawing stream. | READY FOR REVIEW | Awaiting online API integration once classifier model weights are merged.
2026-07-11 | ST-08 | Scrum Master | Standup Logs & Trackers Setup | Establish Excel and Markdown trackers for Standup logs and daily story assignments. | DONE | -
2026-07-11 | ST-01 | Business Analyst | Solution Brief Formulation | Formulate requirements and write the solution proposal brief for YOLOv8 detection & ResNet50 classification. | DONE | -
2026-07-11 | ST-02 | UX Designer | UX Wireframe Layouts Design | Create layout wireframes for the Upload Dashboard and Live Monitoring views. | DONE | -
2026-07-11 | ST-03 | UX Designer | High-Fidelity Mock Screens Design | Define design tokens, HSL colors, Obsidian Dark styling guidelines, and card hover interactions. | DONE | -
2026-07-11 | ST-04 | Solution Architect | Wireframe Feasibility Audit | Review UX wireframes for coordinates mapping scalability and live frame rate throttling bounds. | DONE | -
2026-07-11 | ST-05 | ML Engineer | ResNet50 Classifier Training | Audit dataset splits, setup torch configurations, and run training comparison for 10/20/30/40/50 epochs. | DONE | -
2026-07-11 | ST-06 | Backend Developer | Django API & Views Setup | Initialize django backend, write REST endpoints, and implement YOLOv8 detection/crop views. | DONE | -
2026-07-11 | ST-07 | Frontend Developer | Angular UI Components Coding | Initialize Angular app, build CarDetectionService, Dashboard upload views, and LiveCamera canvas drawing stream. | DONE | -
2026-07-11 | ST-08 | Scrum Master | Standup Logs & Trackers Setup | Establish Excel and Markdown trackers for Standup logs and daily story assignments. | DONE | -
2026-07-11 | ST-01 | Business Analyst | Solution Brief Formulation | Formulate requirements and write the solution proposal brief for YOLOv8 detection & ResNet50 classification. | DONE | -
2026-07-11 | ST-02 | UX Designer | UX Wireframe Layouts Design | Create layout wireframes for the Upload Dashboard and Live Monitoring views. [Linked Diagram: docs/architecture_flow.svg] | DONE | -
2026-07-11 | ST-03 | UX Designer | High-Fidelity Mock Screens Design | Define design tokens, HSL colors, Obsidian Dark styling guidelines, and card hover interactions. [Linked Mockup: docs/ux_ui_design.svg] | DONE | -
2026-07-11 | ST-04 | Solution Architect | Wireframe Feasibility Audit | Review UX wireframes for coordinates mapping scalability and live frame rate throttling bounds. [Linked Flow: docs/architecture_wireframe.md] | DONE | -
2026-07-11 | ST-05 | ML Engineer | ResNet50 Classifier Training | Audit dataset splits, setup torch configurations, and run training comparison for 10/20/30/40/50 epochs. | DONE | -
2026-07-11 | ST-06 | Backend Developer | Django API & Views Setup | Initialize django backend, write REST endpoints, and implement YOLOv8 detection/crop views. | DONE | -
2026-07-11 | ST-07 | Frontend Developer | Angular UI Components Coding | Initialize Angular app, build CarDetectionService, Dashboard upload views, and LiveCamera canvas drawing stream. | DONE | -
2026-07-11 | ST-08 | Scrum Master | Standup Logs & Trackers Setup | Establish Excel and Markdown trackers for Standup logs and daily story assignments. | DONE | -